## Sheet1
SPRINT | TASK ID | TASK NAME (FEATURE) | ASSIGNED TO | START | FINISH | PRIORITY | STATUS | ASSIGNED TO SPRINT
Sprint 1 |  |  |  | 2025-02-03 | 2025-02-17 |  | Not Started
| 1.1 | Select the application Medium | Kameron Smith and Walker (Mentor) | 2025-02-03 | 2025-02-04 | High | Complete | Yes | This section is for the drop-down list
| 1.2 | Set Up environment | Everyone | 2025-02-04 | 2025-02-16 | Medium | In Progress | Yes | Yes | High | Complete
| 1.3 | Select the language to be utilized | Walker (Mentor) | 2025-02-07 | 2025-02-07 | High | Complete | Yes | No | Medium | In Progress
| 1.4 | [8 empty] | Low | Not Started
1.5
1.6
Sprint 2 |  |  |  | 2025-02-17 | 2025-03-03
2.1
Sprint 3 |  |  |  | 2025-03-03 | 2025-03-17
3.1
Sprint 4 |  |  |  | 2025-03-17 | 2025-03-31
4.1
Sprint 5 |  |  |  | 2025-03-31 | 2025-04-14
5.1
Formulas:
FINISH = [START]+(7*2)