## Sheet1
FA2024 CSC154 Group Project Schedule
Milstone | Tasks | Date | Assignments | Due Date
Sprint 1 09/16/2024 – 10/06/2024 | Team project kickoff | 09/16/2024 - 09/22/2024 | Week 1 progress status report | 09/24/2024
| Project selection and development plan | 09/23/2024 - 09/29/2024 | Week 2 progress status report | 09/29/2024
|  | 09/30/2024 - 10/06/2024 | Week 3 progress status report | 10/06/2024
|  |  | Group Project Overview | 10/06/2024
Sprint 2 10/07/2024 – 10/20/2024 | Project requirements specification | 10/07/2024 - 10/13/2024 | Week 1 progress status report | 10/13/2024
|  | 10/14/2024 - 10/20/2024 | Week 2 progress status report | 10/20/2024
|  |  | Group project requirements specification Version 1 | 10/20/2024
Sprint 3 10/21/2024 – 11/03/2024 | Project high-level design | 10/21/2024 - 10/27/2024 | Week 1 progress status report | 10/27/2024
|  | 10/28/2024 - 11/03/2024 | Week 2 progress status report | 11/03/2024
|  |  | Group project requirements specification Version 2 | 11/03/2024
Sprint 4 11/04/2024 – 12/08/2024 | Project presentation and evaluation | 11/04/2024 - 11/10/2024 | Week 1 progress status report | 11/10/2024
|  | 11/11/2024 - 11/17/2024 | Week 2 progree status report | 11/17/2024
|  |  | Group project presentation documentation | 11/17/2024
|  | 11/18/2024 - 11/24/2024 | Project presentation and evaluation | 11/24/2024
|  | 12/02/2024 - 12/08/2024 | Project presentation and evaluation | 12/08/2024